## Sheet1
|  | Project Name: | Inventory Management System
|  | Project Description: | Creating a working IMS using java with an SQL database
|  | Project Owner: | Robert Tolley
Risk ID | Date registered | Risk area | Risk description | Probability |  |  | Risk Level |  |  | Project impact | Proximity / Length of impact | Response strategy
1 | 18.12.20 | covid-19 | wide spread virus |  |  | x |  | x |  | Potentially bed ridden Cold like symptoms | 2 weeks | Work when feeling better inform trainer
2 | 18/12.20 | damaged / broken laptop | potentially broken screen, keyboard, mouse or unable to boot laptop | x |  |  |  |  | x | Unable to complete or present presentation | 1 week | ask to be provided with a QA laptop
3 | 18/12/20 | eye strain | sitting staring at the screen for long periods of time |  |  | x | x |  |  | may require a short break away from the computer | 30 mins | Take a short break away from computer
4 | 18/12/20 | distractions | Distractions around the room I work in |  | x |  |  | x |  | may slow down work progress unless addressed early | hours | reduce the distraction probability around the room by removing them and setting assigned work time & break times
5 | 18/12/20 | internet connection | internet connection dropping or running slow | x |  |  | x |  |  | may result in longer load up times for project assets or for some project assets to be inaccessible | 30 mins - 1 day | if internet drops - seek out broadband help if internet is slow for a long period of time - reset router
6 | 18/12/20 | tiredness | may be tired in the mornings or later on in the evenings |  |  | x | x |  |  | slower work pace more mistakes | 30 mins | ensure full nights reset night before start early so that not working too late at night
7 | 18/12/20 | family medical emergency | may be required to take a family member to the hospital or visit said member in the hospital | x |  |  |  | x |  | Require me to take the day to drive family member or to visit said family member | 1 day | allow trainer to know of the circumstances leading to my absence
8 | 18/12/20 | Lack of knowledge | Required section in project may use unknow areas to me |  |  | x |  |  | x | This may take up more time for certain areas of the project leaving less time for others | 4 hours | use the QA community or speak to a trainer about the area being found difficult
9
10